## Sheet1
WEEK
TEAM | 1 | 2 | 3 | 4 | 5-4/27 | DEMO 4/29 | 6 | 7 | 8 | 9 | 10
Manufacturing | N/A | 1.Revised Alpha, 2.McMaster components ordered 3.Waterjetting complete | 1.Finish Manufacturing Parts 2.80/20 Frame assembled | 1.Fully Assemlbed Prototype: Frame, Mechanism, Tablet and Magnet | Solve any problems that come up, help others integrate into alpha prototype
Magnet | 1. Air Bearing Demo - compare it with current magnets 2. Decide needed measurements 3. Decide measurement methods | 1. Do necessary measurements 2. Decide between air bearing / thrust bearings | 1. Build final work-like prototype 2. Ideate user experience: pucks/ gloves? | 1. Prototype improvements to user experience 2. User testing | 1. Magnet Assembled onto Alpha prototype
Electronics | N/A | 1. wiring touchscreen with raspberry pi, | 1. Integration with embedded Software | 1.Wire limit swtiches 2. Write code to detect limit switch activation 3. Integrate with embedded code | Control Demo ready
Embedded | N/A | Change from python to C++ to attempt to improve loop speed | Integration with touchscreen | 1. Unpolished first demo | Control Demo ready